## Cover Page
Work Breakdown Structure
Cloud-based National
Health Record Exchange
Thabo Morenammele
Lerotholi Polytechnic | School of Engineering

## WBS
#NAME?
Work Breakdown Strcture
Done
In-progress
Delayed
| Today |  |  | 2026-03-15
| Project Team Name |  |  | Thabo Morenammele
| Project Topic |  |  | Cloud-based National Health Record Exchange
| Task |  |  |  | Start date | End date | Responsibility | Deliverable | Task Status | W1 |  |  |  |  | W2 |  |  |  |  | W3 |  |  |  |  | W4
[10 empty] | D1 | D2 | D3 | D4 | D5 | D6 | D7 | D8 | D9 | D10 | D11 | D12 | D13 | D14 | D15 | D16 | D17 | D18 | D19 | D20
[10 empty] | 2021-11-01 | 2021-11-02 | 2021-11-03 | 2021-11-04 | 2021-11-05 | 2021-11-06 | 2021-11-07 | 2021-11-08 | 2021-11-09 | 2021-11-10 | 2021-11-11 | 2021-11-12 | 2021-11-13 | 2021-11-14 | 2021-11-15 | 2021-11-16 | 2021-11-17 | 2021-11-18 | 2021-11-19 | 2021-11-20
| 1. Project Planning |  |  |  | 23/02/2026 | 28/02/2026 |  |  | Done | bar: 2021-11-01 to 2021-11-05
|  | 1.1. | Project Scope |  | 22/09/2025 | 26/09/2025 |  |  | Done | bar: 2021-11-01 to 2021-11-05
|  |  | 1.1.1. Sub-title | Objectives | 22/09/2025 | 26/09/2025 |  |  | Done | bar: 2021-11-01 to 2021-11-05
|  |  |  | 1.1.1.1. Business Model Canvas, WBS | 22/09/2025 | 26/09/2025 | Thabo Morenammele | Project scope, objective, WBS, Business Model Canvas | Done | bar: 2021-11-01 to 2021-11-05
| 2. Requirements Analysis | [7 empty] | Done
|  | 2.1 | Gather System requirements |  | 2026-02-03 | 2026-06-03 |  |  | Done | bar: 2021-11-06 to 2021-11-10
|  |  | 2.1.1 | Identify steakholders | 2026-02-03 | 2026-03-03 | Thabo Morenammele | Stakeholder list | Done | bar: 2021-11-06 to 2021-11-10
|  |  | 2.1.2 | Analyze Healthcare workflow | 2026-03-03 | 2026-04-03 | Thabo Morenammele | Requirement analysis | Done | bar: 2021-11-06 to 2021-11-10
|  |  | 2.1.3 | Finalize software requirement Specification Document | 2026-04-03 | 2026-06-03 | Thabo Morenammele | Requirement list | Done | bar: 2021-11-06 to 2021-11-10
3. System Design
|  | 3.1 | Design System Architecture |  | 2026-09-03 | 13/3/2026 | Thabo Morenammele |  | In-progress | bar: 2021-11-11 to 2021-11-15
|  |  | 3.1.1 | Database Design (ERD) | 2026-09-03 | 2026-09-03 | Thabo Morenammele | ER Diagram | In-progress | bar: 2021-11-11 to 2021-11-15
|  |  | 3.1.2 | UI/UX design mockups | 2026-10-03 | 2026-11-03 | Thabo Morenammele | UI prototypes | In-progress | bar: 2021-11-11 to 2021-11-15
|  |  | 3.1.3 | Finalization of UML diagrams | 2026-12-03 | 13/3/2026 | Thabo Morenammele | Architecture diagrams | In-progress | bar: 2021-11-11 to 2021-11-15
| 4. Backend Development | [7 empty] | In-progress
|  | 4.1 | Setup Cloud server | [5 empty] | In-progress
|  |  | 4.1.1 | Implement Authentication and roles | 16/3/2026 | 18/3/2026 | Thabo Morenammele | Login system | In-progress | bar: 2021-11-16 to 2021-11-20
|  |  | 4.1.2 | Patient registration, medical records management, medication module development | 19/3/2026 | 20/3/2025 | Thabo Morenammele | Registration system, EHR records, Orders & results | In-progress | bar: 2021-11-16 to 2021-11-20
5. Frontend Development
|  | 5.1 | Dashboard and Portal
|  |  | 5.1.1 | Clinician dashboard | 23/3/2026 | 25/3/2026 | Thabo Morenammele | Dashboard UI | In-progress
|  |  | 5.1.2 | Patient search and profile page | 26/3/2026 | 26/3/2026 | Thabo Morenammele | Patient interface | In-progress
|  |  | 5.1.3 | Patient Portal | 26/3/2026 | 27/3/2026 | Thabo Morenammele | Portal interface | In-progress
6. System Integration
|  | 6.1 | Integrate frontend and frontend
|  |  | 6.1.1 | Database integration and DHIS2 API integration | 30/3/2026 | 2026-02-03 | Thabo Morenammele | Data exchange and connection | In-progress
7. Testing
|  | 7.1 | Functional testing
|  |  | 7.1.1 | Security and perfomance testing | 2026-04-04 | 2026-10-04 | Thabo Morenammele | Security valuation and perfomance report | In-progress
8. Deployment
|  | 8.1 | Deploy system to cloud
|  |  | 8.1.1 | Configure backups and security | 2026-10-04 | 20/4/2026 | Thabo Morenammele | Backup systems | In-progress